## Lookups
User Story Owner's List
Bold | <b> | </b><br /> |  |  |  | First Name | Last Name | Email Address | Role
CRLF | <br /><br /> | [7 empty] | DBA
DE
TeamNames | [8 empty] | PO
|  | Start Date | End Date | Release | Iteration |  |  |  | PO
North Stars |  | 2019-02-03 | 2019-02-16 | Release 18 | R18 Sprint 1 |  |  |  | SM
Phoenix Fire |  | 2019-02-17 | 2019-03-02 | Release 18 | R18 Sprint 2 |  |  |  | DBA
Castellan |  | 2019-03-03 | 2019-03-16 | Release 18 | R18 Sprint 3 | Charles | Colstom | charles.colstrom@optum.com | DNU
Chanakya |  | 2019-03-17 | 2019-03-30 | Release 18 | R18 Sprint 4 |  |  |  | DBA
EMPP |  | 2019-03-31 | 2019-04-13 | Release 18 | R18 Sprint 5 |  |  |  | PO
|  | 2019-04-14 | 2019-04-27 | Release 19 | R19 Sprint 1 |  |  |  | DBA
|  | 2019-04-28 | 2019-05-11 | Release 19 | R19 Sprint 2 |  |  |  | DE
|  | 2019-05-12 | 2019-05-25 | Release 19 | R19 Sprint 3 |  |  |  | CBV
|  | 2019-05-26 | 2019-06-08 | Release 19 | R19 Sprint 4 | Kim | Rook | kim.rook@optum.com | SM
|  | 2019-06-09 | 2019-06-22 | Release 19 | R19 Sprint 5 |  |  |  | eBiz
Project Type | Name | 2019-06-23 | 2019-07-06 | Release 20 | R20 Sprint 1 |  |  |  | DBA
| None | 2019-07-07 | 2019-07-20 | Release 20 | R20 Sprint 2 |  |  |  | Perf
Pol | Polaris | 2019-07-21 | 2019-08-03 | Release 20 | R20 Sprint 3 |  |  |  | BLD
CA | Cloud Adoption | 2019-08-04 | 2019-08-17 | Release 20 | R20 Sprint 4 |  |  |  | SM
E&I | E and I | 2019-08-18 | 2019-08-31 | Release 20 | R20 Sprint 5 |  |  |  | PO
PL | Program lvl | 2019-09-01 | 2019-09-14 | Release 21 | R21 Sprint 1 |  |  |  | DNU
M&V | M and V | 2019-09-15 | 2019-09-28 | Release 21 | R21 Sprint 2 |  |  |  | CBV
Pro | Provider | 2019-09-29 | 2019-10-12 | Release 21 | R21 Sprint 3 |  |  |  | Perf
IHR | IHR | 2019-10-13 | 2019-10-26 | Release 21 | R21 Sprint 4 |  |  |  | BLD
PLM | PLM | 2019-10-27 | 2019-11-09 | Release 21 | R21 Sprint 5 |  |  |  | DBA
M&A | Merger & Acquisition | 2019-11-10 | 2019-11-23 | Release 22 | R22 Sprint 1 | Sean | Gillespie | sean_gillespie@optum.com | PO
|  | 2019-11-24 | 2019-12-07 | Release 22 | R22 Sprint 2 |  |  |  | BLD
|  | 2019-12-08 | 2019-12-21 | Release 22 | R22 Sprint 3 |  |  |  | EBIZ
|  | 2019-12-22 | 2020-01-04 | Release 22 | R22 Sprint 4 |  |  |  | BLD
EBIZ
eBiz
BLD
DBA
BLD
DBA
DNU
DNU
DNU
Capabiliy and Feature Owner's List
[6 empty] | First Name | Last Name | Email Address | Role
[6 empty] | Charles | Colstrom | charles.colstrom@optum.com | TDO
PM
DE
DNU
Formulas:
Start Date = +[Start Date, row above]+14
End Date = +[End Date, row above]+14

## CapFeat-UI
Capability Import Form |  |  | Feature Import Form - Mile Stone level
Input Fields | Values | Formats | Input Fields | Planned Start Date | Duration (Days) | Planned End Date | Release
Project Number | PRJ166463 | PRJxxxxxx | Intial Engagement | 2019-03-06 | 15 | 2019-03-21 | Release 18
Project Type | M&A | <---Select from Drop Down | DEVELOPMENT Env Widgets | 2019-03-21 | 0 | 2019-03-21 | Release 18
Capability Title | M&A_UHOne_Vue_ETS_AHI | No more than 50 chars | TEST Env Widgets | 2019-03-21 | 0 | 2019-03-21 | Release 18
Capability Short Name | AHI | short name (goes after ,) | STAGE Env Widgets | 2019-03-21 | 30 | 2019-04-20 | Release 18
Planned Start Date | 2019-03-06 | mm/dd/ccyy | PRODUCTION Env Widgets | 2019-04-20 | 30 | 2019-05-20 | Release 19
Planned End Date | 2019-12-31 | mm/dd/ccyy | Post Build Configs | 2019-05-20 | 30 | 2019-06-19 | Release 19
Assigned Team | Phoenix Fire | <---Select from Drop Down | Decom Activities | 2019-06-19 | 30 | 2019-07-19 | Release 19
Capabilty Owner | charles.colstrom@optum.com | <---Select from Drop Down | GO-LIVE, Warranty Support Work | 2019-07-19 | 30 | 2019-08-18 | Release 20
Feature Owner | charles.colstrom@optum.com | <---Select from Drop Down | TRUE-UP & Close | 2019-12-31 | 0 | 2019-12-31 | Release 22
Description | As an application owner, I need the following | Free Form <alt>+Enter for CRLF | Grey background cells are Read-Only and should not be changed
Completed: |  | Free Form <alt>+Enter for CRLF
Next Steps: | Setup intro and discovery call with app team | Free Form <alt>+Enter for CRLF
Acceptance Criteria | Confirm hardware and software deployments against application configuration, infrastructure, and architecture requirements. Validate Upgrade Software integrations are properly deployed and the correct components are released and migrated through environment promotion cycles. | Free Form <alt>+Enter for CRLF
In Scope / Out of Scope: |  | Free Form <alt>+Enter for CRLF
Notes: |  | Free Form <alt>+Enter for CRLF
Contacts: |  | Free Form <alt>+Enter for CRLF
Read Only fields that are needed
Input Fields | Values | Formats
Parent Capability Name | PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | RO - Display Only
Parent Feature Name | PRJ166463: Intial Engagement, AHI | RO - Display Only
Parent Feature Name | PRJ166463: DEVELOPMENT Env Widgets, AHI | RO - Display Only
Parent Feature Name | PRJ166463: TEST Env Widgets, AHI | RO - Display Only
Parent Feature Name | PRJ166463: STAGE Env Widgets, AHI | RO - Display Only
Parent Feature Name | PRJ166463: PRODUCTION Env Widgets, AHI | RO - Display Only
Parent Feature Name | PRJ166463: GO-LIVE, Warranty Support Work, AHI | RO - Display Only
Parent Feature Name | PRJ166463: Decom Activities, AHI | RO - Display Only
Parent Feature Name | PRJ166463: TRUE-UP & Close, AHI | RO - Display Only
Formulas:
Planned Start Date = [Planned Start Date, row above]+[Duration (Days), row above]
Planned End Date = IF([Planned Start Date]="","",+Table26[[#This Row],[Planned Start Date]]+Table26[[#This Row],[Duration (Days)]])

## US-UI
Initial Skeleton User Story Import Form
Input Fields | Owner | Planned Start Date | Duration (Days) | Planned End Date | Release | Iteration | Belongs to feature parent
L1-ASK, TMDB, Project Numbers Created | kim.rook@optum.com | 2019-03-06 | 5 | 2019-03-11 | Release 18 | R18 Sprint 3 | PRJ166463: Intial Engagement, AHI
SLD designed and approved | sean_gillespie@optum.com | 2019-03-11 | 10 | 2019-03-21 | Release 18 | R18 Sprint 3 | PRJ166463: Intial Engagement, AHI
Estimate created and approved | kim.rook@optum.com | 2019-03-11 | 5 | 2019-03-16 | Release 18 | R18 Sprint 3 | PRJ166463: Intial Engagement, AHI
Initiate EIS Early Engagement Identification | sean_gillespie@optum.com | 2019-03-11 | 5 | 2019-03-16 | Release 18 | R18 Sprint 3 | PRJ166463: Intial Engagement, AHI
Ops Readiness Initial Review | kim.rook@optum.com | 2019-03-21 | 2 | 2019-03-23 | Release 18 | R18 Sprint 4 | PRJ166463: Intial Engagement, AHI
(PLACEHOLDER) Build and Deliver DEVELOPMENT Widgets | sean_gillespie@optum.com | 2019-03-21 | 0 | 2019-03-21 | Release 18 | R18 Sprint 4 | PRJ166463: DEVELOPMENT Env Widgets, AHI
(PLACEHOLDER) Build and Deliver TEST Widgets | sean_gillespie@optum.com | 2019-03-21 | 0 | 2019-03-21 | Release 18 | R18 Sprint 4 | PRJ166463: TEST Env Widgets, AHI
(PLACEHOLDER) Build and Deliver STAGE Widgets | sean_gillespie@optum.com | 2019-03-21 | 30 | 2019-04-20 | Release 18 | R18 Sprint 4 | PRJ166463: STAGE Env Widgets, AHI
(PLACEHOLDER) Build and Deliver PRODUCTION Widgets (1 of 2) | sean_gillespie@optum.com | 2019-04-20 | 30 | 2019-05-20 | Release 19 | R19 Sprint 1 | PRJ166463: PRODUCTION Env Widgets, AHI
(PLACEHOLDER) Build and Deliver PRODUCTION Widgets (2 of 2) | sean_gillespie@optum.com | 2019-04-20 | 30 | 2019-05-20 | Release 19 | R19 Sprint 1 | PRJ166463: PRODUCTION Env Widgets, AHI
Add Servers to CBV Chargeback Record | kim.rook@optum.com | 2019-05-20 | 1 | 2019-05-21 | Release 19 | R19 Sprint 3 | PRJ166463: PRODUCTION Env Widgets, AHI
Ops Readiness Final Review | kim.rook@optum.com | 2019-07-19 | 2 | 2019-07-21 | Release 20 | R20 Sprint 2 | PRJ166463: GO-LIVE, Warranty Support Work, AHI
Prework for Go-Live (mm/dd/yy), Warranty End Date (mm/dd/yy) | kim.rook@optum.com | 2019-07-19 | 1 | 2019-07-20 | Release 20 | R20 Sprint 2 | PRJ166463: GO-LIVE, Warranty Support Work, AHI
Decom Work | kim.rook@optum.com | 2019-12-31 | 10 | 2020-01-10 | Release 20 | R20 Sprint 3 | PRJ166463: Decom Activities, AHI
Project Close-Out | kim.rook@optum.com | 2019-12-31 | 1 | 2020-01-01 | Release 20 | R20 Sprint 3 | PRJ166463: TRUE-UP & Close, AHI
This are Read-Only cells and should not be changed
Feature Reference Data
| Input Fields | Planned Start Date | Duration (Days) | Planned End Date | Release
| Intial Engagement | 2019-03-06 | 15 | 2019-03-21 | Release 18
| IB&D DEVELOPMENT Env Widgets | 2019-03-21 | 0 | 2019-03-21 | Release 18
| IB&D TEST Env Widgets | 2019-03-21 | 0 | 2019-03-21 | Release 18
| IB&D STAGE Env Widgets | 2019-03-21 | 30 | 2019-04-20 | Release 18
| IB&D PRODUCTION Env Widgets | 2019-04-20 | 30 | 2019-05-20 | Release 19
| GO-LIVE, Warranty Support Work | 2019-07-19 | 30 | 2019-08-18 | Release 20
| Decom Activities | 2019-12-31 | 0 | 2019-12-31 | Release 22
| TRUE-UP & Close | 2019-12-31 | 0 | 2019-12-31 | Release 22
Formulas:
Planned Start Date = +[Planned Start Date, row above]+[Duration (Days), row above]
Planned Start Date = +[Planned Start Date, row above]
Planned End Date = IF([Planned Start Date]="","",+Table9[[#This Row],[Planned Start Date]]+Table9[[#This Row],[Duration (Days)]])

## CapImport
Name | PlannedStartDate | PlannedEndDate | Description | LeadTeam | PPM Optics ID (PRJxxxxxx) | State | Owner | Project
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | 2019-03-06 | 2019-12-31 | As an application owner, I need the following <br /><br /><b>Completed: </b><br /><br /><br /><b>Next Steps: </b><br />Setup intro and discovery call with app team<br /><br /><b>Acceptance Criteria </b><br />Confirm hardware and software deployments against application configuration, infrastructure, and architecture requirements. Validate Upgrade Software integrations are properly deployed and the correct components are released and migrated through environment promotion cycles.<br /><br /><b>In Scope / Out of Scope: </b><br /><br /><br /><b>Notes: </b><br /><br /><br /><b>Contacts: </b><br /> | Phoenix Fire | PRJ166463 | Capability Created | charles.colstrom@optum.com | Phoenix Fire

## FeatImport
Parent | Name | Description | Project | Release | Environment | Feature Delivery Type | Preliminary Estimate | PlannedStartDate | PlannedEndDate | PPMOpticsIDPRJxxxxxx | LeadTeam | STATE | Tags | Owner
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: Intial Engagement, AHI | <p>As application team member I want to have all the&nbsp; initial request numbers in place so I can have my app built to support&nbsp;my business customers</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria:</font><br /><font color="#ffffff" style="background-color: rgb(255, 0, 0);"><font color="#000000" style="background-color: rgb(255, 255, 255);">ASK, TMDB, PROJECT numbers created and validated they are in PPM Optics, ASK, ESC, and vRops<br />EDR tier rating and RTO defined<br />SLD Created, approved by app and SE team<br />Estimate created,&nbsp;approved by app team and standard estimation&nbsp;approval process</font><br /></font></p><p><br /></p> | Phoenix Fire | Release 18 | Not Applicable | Non-Deliverable | M | 2019-03-06 | 2019-03-21 | PRJ166463 | Phoenix Fire | Feature Created | NPS Estimate NPS Design | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: DEVELOPMENT Env Widgets, AHI | <p>As Application team member, I want my DEV environment built out to support my business customers</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria</font><br />&nbsp;&nbsp; App team have logged onto and verified servers are built to their requirements. <br />&nbsp;&nbsp; Correct access / permissions are in place for the application team</p> | Phoenix Fire | Release 18 | Development |  | M | 2019-03-21 | 2019-03-21 | PRJ166463 | Phoenix Fire | Feature Created |  | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: TEST Env Widgets, AHI | <p>As Application team member, I want my TST environment built out to support my business customers</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria</font><br />&nbsp;&nbsp; App team have logged onto and verified servers are built to their requirements. <br />&nbsp;&nbsp; Correct access / permissions are in place for the application team</p> | Phoenix Fire | Release 18 | Test |  | M | 2019-03-21 | 2019-03-21 | PRJ166463 | Phoenix Fire | Feature Created |  | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: STAGE Env Widgets, AHI | <p>As Application team member, I want my STG environment built out to support my business customers</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria</font><br />&nbsp;&nbsp; App team have logged onto and verified servers are built to their requirements. <br />&nbsp;&nbsp; Correct access / permissions are in place for the application team</p> | Phoenix Fire | Release 18 | Stage |  | M | 2019-03-21 | 2019-04-20 | PRJ166463 | Phoenix Fire | Feature Created | NPS NonProd | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: PRODUCTION Env Widgets, AHI | <p>As Application team member, I want my PRD environment built out to support my business customers</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria</font><br />&nbsp;&nbsp; App team have logged onto and verified servers are built to their requirements. <br />&nbsp;&nbsp; Correct access / permissions are in place for the application team</p> | Phoenix Fire | Release 19 | Production |  | M | 2019-04-20 | 2019-05-20 | PRJ166463 | Phoenix Fire | Feature Created | NPS Prod | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: Post Build Configs, AHI | <p>As Application team member, I want my environments to be setup with all post config setups for the new application are complete. This may include Firewall Rules, F5, etc...</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria</font><br />&nbsp;&nbsp; Post Config items identified in SLD completed <br /></p> | Phoenix Fire | Release 19 | Not Applicable | Non-Deliverable | M | 2019-05-20 | 2019-06-19 | PRJ166463 | Phoenix Fire | Feature Created |  | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: Decom Activities, AHI | <p>As a member of the project team, I need all project completion activities done so the project can be marked complete in all systems.</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria</font><br />&nbsp;&nbsp; Project chargeback validation team engaged. <br />&nbsp;&nbsp; Any necessary server decommissions are submitted</p> | Phoenix Fire | Release 20 | Not Applicable | Non-Deliverable | M | 2019-06-19 | 2019-07-19 | PRJ166463 | Phoenix Fire | Feature Created |  | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: GO-LIVE, Warranty Support Work, AHI | <p>As Application team member I need to Go-live work completed and 30 day Warranty support from all involved parties to make sure this project is successful</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria:</font><br />For Go -Live and 30 day warranty support: make sure all necessary work is completed to keep app running in production</p> | Phoenix Fire | Release 20 | Not Applicable | Non-Deliverable | M | 2019-07-19 | 2019-08-18 | PRJ166463 | Phoenix Fire | Feature Created | NPS Go-Live | charles.colstrom@optum.com
PRJ166463: M&A-M&A_UHOne_Vue_ETS_AHI | PRJ166463: TRUE-UP & Close, AHI | <p>As Application team member I want to have all my project upgrades complete so that the application&nbsp;can support my business customers</p><p><font color="#ffffff" style="background-color: rgb(255, 0, 0);">Acceptance Criteria:</font></p><p>All work is completed based on SLD and project charter</p><p>All devices are in production status</p><p>Operational Readiness plan completed<br /></p> | Phoenix Fire | Release 22 | Not Applicable | Non-Deliverable | M | 2019-12-31 | 2019-12-31 | PRJ166463 | Phoenix Fire | Feature Created |  | charles.colstrom@optum.com