## Summary
Release Automation Upgrade Checklist
This document is a guideline for upgrading Release Automation. Before starting you will need to determine two key pieces of information:
1 | Verify the version of Release Automation that is currently installed, including Build
2 | Determine what version of Release Automation you wish to upgrade to
Next, review the chart below and determine if one or multiple upgrades will be required. For example, if you are currently at Version 4.7.1 and you want to upgrade to Version 6.2:
1 | First, you will need to upgrade RA 4.7.1 to RA 5.5.x
2 | Next, you will need to upgrade from RA 5.5.x RA 6.1
3 | Finally, you will need to upgrade from RA 6.1 to RA 6.2
Note: Before upgrading from RA 4.7.1 applications should be reviewed to understand the changes that will be affected by the modification to the environment mechanism.
Diagram Notes:
* | Before upgrading from RA 4.7.1 you should run the “Pre-upgrade Discovery Utility” which will help identify the parameters and artifacts that will need to be updated as part of the design change within RA 5.0.x – This Utility can ONLY be executed BEFORE the upgrade on RA 4.7.1
* | Upgrade from 5.0.0 to 5.5.2 (Linux / Oracle) – during upgrade jms.properties file is not properly updated, one line is missed (jms.transport.port.nac=61617)
* | Upgrade to RA 6.1 is supported from 5.0.2 only … not from 5.0.0 or 5.0.1
* | Upgrade to RA 6.2 requires RA 6.1.0 as a baseline. In other words, RA 6.1.0 is mandatory for any upgrade path moving forward, which currently is RA 6.2
Before you start:
* | Plan your upgrade and then Test your Upgrade Plan
* | Based upon the testing results, revise your Upgrade Plan
* | Plan for Failure and devise a Rollback Plan
* | Test your Rollback Plan
* | Plan and execute cold backup of the database and the NAC folder structure
* | Check the Patch Release level and make sure all patches have been applied using the appropriate release installer to perform upgrade
* | Validate and HW/OS requirements for the planned upgrade release to see if anything has changed
For example: as RA 6.1 requires the product server components to run Java 8, some OS platforms which do not support this Java release and cannot be upgraded (nor can they be used for new install of this release)
* | Agent upgrade is not mandatory in case you have upgraded from 5.5.1/5.5.2/6.0.0 to 6.1.0 or 6.2.0 as long as the Agents are at RA 5.5.1 build 1312
* | When upgrading Agents to RA 6.2, Java will be updated to Java 8
* | CI plugins are not part of the core product and their release train is not on the same level. So outside of validating, there is nothing to upgrade or do with those. Customer will need to uninstall and then install the updated plugin if needed.
* | We upgrading Windows Agents there may be an issue with the Windows “Application Experience” Service which will cause the Agent Upgrade to fail
Document Contents (TAB):
General Upgrade Plan – a very general idea of what is involved when performing an upgrade
Pre-Upgrade Tasks – list of tasks that you should consider and perform before upgrading
Step-by-Step Upgrade Plan – detailed list of actual upgrade activities
Rollback Plan – steps to perform if you must rollback your upgrade
Post Upgrade Activities – tasks that should be performed once upgrade is completed
Hardware Requirements – hardware requirements if upgrading to RA 5.5.2 or RA 6.1
Note: |  | All High Availability (HA) related tasks are highlighted in Yellow

## General Upgrade Plan
General Upgrade Plan
Before Starting the Upgrade
1 | User Outage announcement
2 | Disable User Interface Load Balancer (if required)
3 | Disable Command Interface Plugins or External systems
4 | Ensure no Deployments are in Progress and that no Jobs are scheduled to run
5 | Stop RA Management Server or Servers if this is an HA environment
6 | Pause Database Mirroring (If required)
7 | Back up the database
8 | Backup the ActionsLib folder on the NAC or take a complete backup / snapshot of the NAC server
Upgrade
9 | Upgrade the NAC (if this is a HA environment then only do the Primary NAC at this time)
10 | Upgrade a single Execution Server
11 | Upgrade a few Agents to Test Application Deployment
12 | Test Application Deployment
13 | Validate upgrade is successful, if not go to Rollback (Step 20 below)
14 | If this is an HA environment then upgrade the Secondary NAC
15 | If this is an HA environment then the Secondary NAC will be primary, so to Primary NAC
16 | Upgrade Remaining Execution Servers
17 | Upgrade CI Plugins
18 | Enable CI Plugins
19 | Upgrade Remaining Agents
Rollback
20 | Stop NAC and NES
21 | Restore database to previous version
22 | Revert NAC/NES to backup or uninstall and reinstall previous version of RA
23 | Upgrade (uninstall and reinstall) Agents
24 | Start NAC and NES
25 | Enable CI Plugins

## Pre-Upgrade Tasks
Pre-Upgrade Tasks
1 | Create Upgrade Plan which should include or take into consideration these documents:
| 1a | Hardware and Software Requirements – based upon Version that is being upgrade to
| 1b | Detailed Plan – use the Step-by-Step Upgrade Plan as a guide, add additional task as needed along with assignments and dates
| 1c | Contact List – With name, email, and phone of all people involved, Stakeholders, and CA Support (SWAT) – there is an example on the last page of this document
2 | Create Testing Plan and configure Test Environment to mimic Production Environment
3 | Check the see if the “Run As User” functionality is using sudo, if so verify configuration files won’t be overwritten or backup and then restore after upgrade
4 | Review any custom Action Packs or RDK Action Packs prior to upgrading
5 | Look at Rollback Plan and modify according to your environment
6 | Share the Plan and setup meetings with all key individuals on Contact List (Stakeholders and CA)
7 | Update Plan accordingly and establish Testing Plan
8 | Request DBA coverage on upgrade days and provide information related to upgrade
9 | Request Infrastructure (Operations) team cover on upgrade days and provide information related to upgrade
10 | Request CA SWAT and Support team cover on upgrade days and provide information related to upgrade
11 | Initiate all Change Management Requests, confirm that they are signed off on and approved
12 | Ensure the required Ports are available for new version (Post 5.x)
| 12a | TCP Port 61616 between NAC and all Execution servers.
| 12b | TCP Port 8083 between the Web browser (ROC) and NAC connection, this port is required when using the Action pack manager screen
13 | Validate the HW requirements for the upgrade and Load Balancer configuration for HA
14 | Download the latest version of RA from CA and place the media on NAC and NES servers.
15 | Send an email with important dates of planned Upgrade activity to all Stakeholders.
16 | Send mail with RA Agent pre-requisite details to all application teams and request them to validate that target servers meet the Pre-requisites.
17 | App teams to ensure that agents are up and running during the upgrade window.
18 | If there are any monitoring systems on RA agent in target servers, respective App teams have to ensure that it is turned off, to ignore alerts during Upgrade activity.
19 | Communicate to application teams on DB cut-off for upgrading instance
20 | Get signoff from each application team that they validated their target servers meets the Agent Pre-requisites and ready for upgrade.
21 | Check with DB team on space availability in DB server for the additional space required
22 | Send a reminder about that planned Upgrade activity to all Stakeholders, DBA, Infrastructure team and necessary teams
23 | Backup of all existing RA processes.
24 | Determine test to run for verification in Production when upgrade has completed, this is to determine if upgrade is successful or Rollback Plan should be implemented
25 | For RA Version below 5.0 run Utility program to determine what parameters will be impacted by an upgrade to RA 5.x and higher , contact Support or SWAT to get this Utility
26 | Verify that the current version or RA is patched to its latest level
27 | Run Database Best Practice Script to clean old entries
28 | Customers need to review any custom action packs or RDK action packs prior to upgrading
29 | The document specifies 5.5.2 a lot we need to remove this and say download the latest version
30 | How does a customer get hold of this utility?

## Step-by-Step Upgrade Plan
Step-by-Step Upgrade Plan
1 | Send out an email notifying all Stakeholders (Contact List) that Upgrade to Production is about to start
2 | Verify that the following network ports are open between the Servers:
| 2a | TCP Port 61616 between all NAC and all Execution servers.
| 2b | TCP Port 8083 between the Web browser (ROC) and all NAC servers, required for Action Pack Manager
3 | Turn off all monitoring systems that will setoff alerts once the upgrade activity start
4 | Backup Database
5 | Backup these 3 files especially if changes have been made, note these changes will need to be made to new files after Upgrade
| 5a | Server.xml
| 5b | Log4j.properties (also on agents)
| 5c | ApplicationContext-acegi-security.xml
6 | Backup the customer Keystore if a secured connection has been used which is stored in the JRE security folder, note this will need to be updated after the Upgrade
7 | Write down the NAC and NES Service Owners if on Windows backup catalina.sh (Linux) or NolioService.bat (Windows) in case service startup settings are modified
8 | Disable any CI tools to prevent processes being started during the upgrade process
9 | Disable scheduled Processes and Releases
10 | Ensure that there are no active Jobs
11 | Stop User Interface Load Balancing Tool
12 | On NAC stop RA Services, if this is an HA configuration stop services on both NAC Servers
13 | On all NES Servers stop RA services
14 | Backup NAC and NES File Systems
15 | Upgrade all NAC and NES Servers
16 | Verify that RA Services are started on all NAC and NES Servers
17 | Modify these 3 files according to the changes that had been made previously
| 17a | Server.xml
| 17b | Log4j.properties (also on agents)
| 17c | ApplicationContext-acegi-security.xml
18 | Restore or update the customer Keystore if a secured connection is being used which is stored in the JRE security folder
19 | If Windows, Verify that the NAC and NES RA Service Owners are correct
20 | Log into Automation Studio and upgrade a few test “Production” Agents
21 | Verify that these test “Production” Agents have upgraded to the new version
22 | Run verification workflows to assure RA infrastructure is working, this workflow should include design, execution, authorization, and admin activities
23 | Uninstall and Reinstall any CI Server Plugins that are being used and Enable them
24 | Modify the REST calls being used by any external systems
If there are issues determine if the Rollback Plan should be implemented
If Rollback Plan should be implemented pull log files and go to Rollback Plan
If there are no significant issues proceed to next step to finish upgrade and then perform the Post Upgrade Tasks
25 | Upgrade remaining Agents
26 | Enable scheduled Process and Releases
27 | Restart User Interface Load Balancing Tool
28 | Turn on monitoring systems
29 | Send out an email notifying all Stakeholders (Contact List) that Production has been Upgraded

## Rollback Plan
Rollback Plan
1 | Stop all NAC and NES RA Services
2 | Restore Database (full backup)
3 | Restore File Systems to NAC and NES services (use backup created by Upgrade)
4 | Start all NAC RA Services
5 | Uninstall and Reinstall any CI Server Plugins that are being used and Enable them
6 | Log into Automation Studio and upgrade (installs old Agent) to the a few test “Production” Agents that were upgraded
7 | Verify that these test “Production” Agents are at the old version
8 | Run verification workflows to assure RA infrastructure is working
9 | Restart User Interface Load Balancing Tool
10 | Enable scheduled Process and Releases
11 | Turn on monitoring systems
12 | Send out an email notifying all Stakeholders (Contact List) that Production has been Rolled Back

## Post Upgrade
Post Upgrade Tasks
1 | Verify that HA environment is working properly
| 1a | Verify User Interface Load Balancing Tool reverts to Secondary NAC
| 1b | Verify that Primary and Secondary NAC Servers failover properly
| 1c | Verify that Agents are reporting to correct Primary and Secondary NES Server and that if a NES fails the Agents fail over to Secondary NES
2 | Run Deployments on each Application verifying that they work as expected
3 | If RA Version older than 5.0 you may need to modify or reconfigure parameters which are impacted by Upgrade – Utility that was run prior

## Hardware Requirements
Hardware Requirements
Versions 5.5.2 and 6.1
|  | Minimum | Medium | Large
Management Server (NAC)
| CPU | 2 | 4 | 4
| Core per CPU | 2 | 2 | 4
| Memory | 8 GB | 8 GB | 8 GB
| Storage | 40 GB | 100 GB | 250 GB
Database Server
| CPU | 2 | 2 | 2
| Core per CPU | 2 | 2 | 4
| Memory | 8 GB | 8 GB | 8 GB
| Storage | 100 GB | 250 GB | 1 TB
Execution Server (NES)
| CPU | 2 | 2 | 2
| Core per CPU | 1 | 2 | 4
| Memory | 4 GB | 8 GB | 8 GB
| Storage | 40 GB | 100 GB | 250 GB
Repository (Stand Alone)
| CPU | Install | 2 | 2
| Core per CPU | with | 2 | 2
| Memory | Management | 4 GB | 4 GB
| Storage | Server | 100 GB | 100 GB
Agent (Simple)
| CPU | 1 | 1 | 1
| Core per CPU | 1 | 2 | 1
| Memory | 1 GB | 2 GB | 2 GB
| Storage | 10 GB | 40 GB | 40 GB
Agent (Utility or Retrieval)
| CPU | 1 | 1 | 2
| Core per CPU | 1 | 2 | 2
| Memory | 2 GB | 4 GB | 4 GB
| Storage | 40 GB | 100 GB | 100 GB