*Fixed units working time - Markarina *

01-Nov-07 08:08:57

Based on what I have learnt from this forum I was hoping the following would work:-

I have a resource that only works two days a week on a project (Monday/

Tuesday) so I've set max units to 40% (5-day working week) and set the resources calendar so that working hours are 8 hours Monday and 8 hours Tuesday. What I was hoping was that when I assigned the resource to a 16 hour (work) task the duration would be calculated to be 2 days. However the results given by MSP 2007 are somewhat strange.

Duration is calculated as 5 days and the actual period over which the work is done is 15 days. It looks like project has made the assumption that the resource can only work 40% of each day rather than 40% of each week. Likewise a resource with 40% units but who works 5 days a week will still have a duration of 5 days.

Trying to answer my own question it looks like project applies the max units on a per day basis rather than a per week basis, so if you have a resource that is only available to work on a project 2 days per week but these days can vary their is no simple way for project to take this into account given that it applies max units on a per day basis and not a per week basis.

* Fixed units working time - Mike Glen *

01-Nov-07 08:13:56

Hi Markarina,

Welcome to this Microsoft Project newsgroup :)

You need to set the max units to 100% as you will want him to work 100% of the time he is assigned.  His calendar will take care of the two days per week.

FAQs, companion products and other useful Project information can be seen at this web address: http://project.mvps.org/faqs.htm

Hope this helps - please let us know how you get on :)

Mike Glen

MS Project MVP

* Fixed units working time - Markarina *

01-Nov-07 09:30:15

that works for when the days are fixed, but is it possible to achieve if the days in the week that they work sometimes change, essentially we have an engineer working on a number of different projects and the days change depending on each projects schedule, unfortunately it is not possible to link the various project plans together so we can't get around it that way.

* Fixed units working time - Mike Glen *

01-Nov-07 02:12:01

Well, Markarina, if you're having difficulty arranging a schedule with ad hoc assignments, how can you expect Project to do it!  If you want to be that precise, you could keep changing his calendar, but I suggest you use a Usage view and enter the work where you want it to occur.

Mike Glen

Project MVP

* Fixed units working time - Markarina *

02-Nov-07 06:29:16

By the doing it exactly the same way I do, knowing that I have 40% of a persons time in any one week, and that time can be used at any time in one week and not restricted to having that person 40% of every day, but rather 40% in one week, to me straight forward concept that does not appear to be an option in project. I know you can level a project on a week-by-week basis but it seems you can only allocate on a day by day basis

* Fixed units working time - Jan De Messemaeker *

02-Nov-07 07:06:17

To be precise: 40% availability means 24 seconds every minute. It even isn't a day to day option.

Hope this helps,

--

Jan De Messemaeker

Microsoft Project MVP

http://users.online.be/prom-ade

* Fixed units working time - Mike Glen *

02-Nov-07 07:12:37

You can assign by the week if you wish by changing the timescale to weeks (or any other period) in the Resource Usage view.

Mike Glen

Project MVP

.

* Fixed units working time - Steve House *

03-Nov-07 06:01:18

Adding to the others, it is a common misconception that a 40% availability means you have the resource 40% of his work schedule.  While it may average out that way when you look at it from a distance, what 40% availability and assignment level really means is that each unit of duration spent on the task only results in 40% of a unit's worth of work being done.  In other words, assigning a resource 40% to a week-long task means that although the physical activity of the task is effectively proceeding 8 hours per day over the course of a full 5 days the work itself is going slower than normal.

For some reason, perhaps due to having other things on his plate at the same time, the resource is only producing the amount of work over that time period that would have normally taken him 2 8-hour days to accomplish if he had been able to devote his full attention to the task at hand.  For whatever reasoin, the 2 days worth of full-time equivalent work is being spread out over the 5 working days that will transpire between when the task's work starts and when it ends.

If you really want him to work 2 days a week giving the task his full attention, as others have said use a calendar that shows him only working (on the project) two days a week and assign him to tasks 100%.  If the calendar says he works on the project Monday and Tuesday only, assigning him 100% to a two day task will result on it being scheduled for those two days.

If you assign him 100% to a 4 day task, it will result in it being scheduled Mon/Tue this week and Mon/Tue next week.  The fact that you can't predict which two days a week his boss will let you have him is not Project's fault - it's a political issue within your organization, a result of a functional managment-driven organizational model rather than a project managment-driven organization model.  In a fully projectized organization, he would be detached from his home department and temporarily assigned to report to you (or the PMO) for the duration of the project, giving you the ability to freely move him around between various projects and duties, deploying him as you see fit, without having to accomodate his home manager's priorities.  Perhaps you can negotiate to get him on a predictable calendar?  Or better, you pick the two days out of each week to have him that will best meet the needs of the project and then negotiate with his boss on a week by week basis to let you have him those specific days.  For instance, if a predecessor task to one of his happens to end on a Tuesday, it makes most sense to try to have Wednesday as one of the days you can have him in that specific week.  Next week Monday and Thursday might be the best two from the project's perspective. See if you can set up communication with his manager so you can get him when you need him and not when his boss wants to let him go.

--

Steve House [Project MVP]

MS Project Trainer & Consultant

Visit http://www.mvps.org/project/faqs.htm for the FAQs

There is only a limited amount of mind-reading that Project can do for you. You've said your task is a fixed duration task. The duration is the number of working time units between when work is first performed and when it ends. "Fixed duration" for a 5 day task that is presently starting on Monday does not mean regardless of when it starts it will always end on Friday - it means that whenever it starts it will always finish 5 days later. My task is to assemble 50 widgets and I can assemble 10 widgets a day. If I start on Monday, I'll finish the last widget on Friday, 5 days later. But if I get delayed and don't start until Wednesday, that doesn't mean I only have to assemble 30 widgets - I still have to do 50 and I still can only do 10 per day. So the finish date has to change to the following Tuesday because that's when my 5 days of duration will pass after the start on Wednesday AND that really is the earliest possible date that I could finish all 50 of the widgets I'm required to assemble in order to complete the Project's deliverable.

If your task is to do 150 widgets and you assign 3 resources to it, that means each resource will do 50 widgets. Whether they work together or separately, each resource will be required to do 50 widgets. 99% of the time that is an accurate description of the physical nature of the work and Project has no way of knowing if this is one of the 1% that are the exception.

A second misconception evident in your post is just what the task type means and where it has some effect. Fixed duration, fixed work, and fixed units all refer to the identity W=D*U that is at the core of all Project's resource calculations. Remember your basic high school algebra

- any linear equation (y=mx+b) such as this one has a constant, an independent variable, and a dependent variable. You change the independent variable and the equation calculates the dependent variable.

In Project, "b" is zero and so the equation is "y=mx". Project lets you pick what term is the constant, the "m", and what term is the independent variable, the "x". When you're editing a resource assignment, that is changing one of the terms Work, Duration, or Units, the item you are changing is the independent variable and the task type setting instructs Project what to hold constant. If you're changing Units and you want MSP to recalculate work, set the task to fixed duration. If you're changing the Units and want Project to recalculate the duration, set the task type to fixed work. If you're changing the Units and the task type is left on Fixed Units (the default) Project behaves as if the type were Fixed Work this go around. But if you're NOT changing one of the values W, D, or U for resource assignments that have already been made, the task type setting has absolutely no effect whatsoever. In your "problem" example, you weren't changing any of those values when you change the date he starts on the task - the work he's required to do is the same, the duration for your resource is the same, and the units he's assigned are the same - you've merely delayed the start date when he begins to assemble his 50 widgets. And this is crucial to remember, as far as these computations are concerned, Project doesn't know that any other resources assigned to the task even exist.

When you have multiple resources each of them is considered to be independent of all the others and the task duration shown on the Gantt chart is measured from the time the earliest starting resource begins until the latest finishing resource is done. But the W=D*U formula looks at each individual resource in a vacuum. If Joe, Bill, and Fred are all scheduled to start together and work for 10 days, then Bill is delayed a few days, Joe and Fred will start their 10 together and Bill will come in a couple of days after. After Joe and Fred have done their 10 days they go away. Fred continues work by himself after they're gone until he's done his 10 day fair share of the work. The durations for each resource's task have not changed, they're each working for 10 days at 100% doing 1/3 of the total output of the task, just like before and so task type settings have no effect at all, there's nothing to recalculate. What has changed is the total time between when the early bird gets started and the slow bird finishes, ie, the date when all the required work of the task finally gets done. Anything else is going to require hand adjustments on your part.

--

Steve House [MVP]

MS Project Trainer & Consultant