## Testing Plan
Notes: | Items classed as 'Critical' will trigger a rollback |  |  |  |  | Pending
| Items classed as 'Major' will not trigger a rollback and should be resolved in 1 week. |  |  |  |  | Success
| Items classed as 'Minor' will not trigger a rollback and should be resolved in 1 month |  |  |  |  | Fail
Testing Section | Task | Outcome | Class | Action | Comment
Initial Client Testing | Open up firewall to 1 client and test plug-in upgrades | Pending | Critical | Enable "Altiris Maintenance -Ian Laptop" Firewall rule
| Open up firewall to another client and test plug-in upgrades | Pending | Critical
| Confirm Real-Time functionality | Pending | Critical |  | Will agent update be required? Dunno.
| Confirm PCAnywhere functionality | Pending | Critical
Check Fresh Build | Deploy New Machine | Pending | Critical | Use ImageInvoker to deploy current staff build
| Check Agent install and successful upgrade | Pending | Critical
DST User Acceptance | 1. Remote Control | Pending | Critical
| 2. Searching -(a) Partial asset tag | Pending | Critical
| 2. Searching -(b) user name | Pending | Critical
| 2. Searching -(c) IP Address | Pending | Critical
| 2. Searching -(d) MAC Address | Pending | Critical
| 2. Searching -(e) DOMAIN | Pending | Critical
| 2. Searching -(f) Export to CSV | Pending | Critical
| 3. Reports -> Console Worker Reports -> Admin 'ictst' passwords | Pending | Critical
| 4. Resource Manager -Basic inventory | Pending | Critical
| 5. Delete Computers | Pending | Critical
6. The Console Worker Reports
| -->Local Admin ictst passwords | Pending | Major
| -->CONNECT Pilot Group | Pending | Major
| -->Computers Currently Enabled for Cloud Management | Pending | Major
| -->Auto-Deleted Computers | Pending | Major
| -->Add Remove Programs by Name | Pending | Minor | IT Analytics Impersonation Failure
| -->Add Remove Programs Search | Pending | Minor | IT Analytics Impersonation Failure
7. Resource Manager > Inventory
| --> Add Remove Program | Pending | Critical
| --> BIOS | Pending | Critical
| --> User accounts | Pending | Critical
8. Resource Manager
| --> Event logs | Pending | Critical
| --> AexClientLogon | Pending | Critical

## Upgrade Tasks
Pending
Upgrade Step |  | Done? | Action | Comment | Yes
No
Preparation | Firewall off SMP | Pending | Disable "World-Wide Web Services (HTTP Traffic-In)"
|  | Pending | Disable "World-Wide Web Services (HTTPS Traffic-In)"
|  | Pending | Disable "Symantec Management Platform CEM Incoming"
|  | Pending | Disable "Altiris Task Service Tickle (TCP 50123)
|  | Pending | Disable "Altiris SMP task Service (TCP 50124)
| Check Event Queues Empty | Pending | Check C:\ProgramData\Symantec\SMP\EventQueue | Event queue has 400 stuck NSE files. Restarted "Altiris Service" to clear
| Check Windows Event Logs | Pending |  | All OK
| Check SMP Logviewer | Pending |  | All OK
| Confirm local disk free space on SMP | Pending |  | 18GB Free on C:\
| Confirm local disk free space on backend SQL | Pending |  | 60GB Free on C:\
| Backup SQL database | Pending
| Take Snapshot of SMP | Pending
| Take snapshot of SQL Server | Pending
| Upgrade SIM on SMP | Pending
| Reboot SMP (SIM likes a reboot!) | Pending
Install SMP8 Upgrade Prerequsites
| --> Install JRE 8.0 | Pending | Critical | Uninstalled Java 7 Update 79, and then int Java 8 update 212
| --> Install OpenXML SDK 2.0 for MS Office | Pending | Recommended, but not doing on the SMP | For IT Analytics
| --> Install Adobe Flash Player | Pending | Recommended, but not doing on the SMP | For some help video content
| --> update IE to v10 or v11 | Pending | Recommended, but not doing on the SMP (yet) | Will do later
| Start preparing download of SMP8 in SIM | Pending |  | Products to be removed are,
--> Altiris IT Anlalytics SEP pack 21.1.4
--> Altiris Out-Of-Band Management documentation 7.1SP2
--> Symantec Endpoint Protection Integration Component 7.5
--> Symantec Endpoint Protection Integration Component Documentation 7.5
--> Symhelp x64
| Confirm Real-Time functionality | Pending
| Confirm PCAnywhere functionality | Pending
Upgrade SMP | Begin SMP upgrade through SIM | Pending |  | 1.3GB download (10mins). Should take 3hrs to upgrade (Installing 1.5 hour, configuring 1.5 hour)
| Reboot SMP | Pending |  | (Executed 14.20 Saturday)
| Check Windows Event Logs | Pending |  | OK
| Check SMP Logviewer | Pending |  | Nothing terrible there
Hotfix SMP | Apply HF5 through SIM | Pending |  | 1GB of download(10mins).
| Apply DB fix (TECH234452) | Pending |  | Executed (15:24) Finished (16:32)
| Apply Custom DB fix for PcAnywhere | Pending |  | Executed (17:32). PcAnwhere doesn't show up as healthy unless we add a row to the SMPversions table
Configure upgrade policies
| --> SMA Upgrade policy (x64) Enabled (Non SiteServer) | Pending
| --> Software Management Solution Plug-in Upgrade | Pending
| --> Power Scheme task plug-in Upgrade | Pending
| --> Power Scheme task plug-in Install | Pending
| --> Inventory Plugin Upgrade | Pending |  | This policy setting schedule was reset to "Once Only" by the SMP upgrade
| --> Inventory Plugin Install | Pending |  | This policy was disabled by the upgrade
| --> Application Metering for Windows Install | Pending
| --> Application Metering for Windows Upgrade | Pending
Initial Client Testing | Open up firewall to 1 client and test plug-in upgrades | Pending | Enable "Altiris Maintenance -Ian Laptop" Firewall rule
| Open up firewall to another client and test plug-in upgrades | Pending | Enable "Altiris Maintenance -Ian Connect Workstation" Firewall rule
| Confirm Real-Time functionality | Pending
| Confirm PCAnywhere functionality | Pending
Upgrade SiteServer | Install SiteServer Pre-requisites | Pending | Install .NET Framework 4.5.1 on ICT-SITE1
| Enable SiteServer Agent Upgrade Policy | Pending | Enable "Symantec Management Agent for Windows x64 (Site Server Only) Upgrade
| Open up firewall to site server | Pending | Enable "Altiris Maintenance -Site Server" Firewall rule
| Enable Task Server Upgrade policy | Pending | SiteManagement -> Site Server Settings -> Task Service -> Advanced
| Confirm Task Server Upgrade | Pending | Check Agent version on site server
Upgrade CEM | Install CEM Server Pre-requisites | Pending | .NET Framework 4.5.1 already installed on Cloud Gateway (required for Installer!)
| Upgrade CEM Internet Gateway Package | Pending | Now on Apache 2.2.29, OpenSSL 1.0.1u-fips, SMP Gateway 8.0.3577.0
| Test Cloud Agent switching between CEM active and inactive | Pending | Have remote laptop direct connect (by opening up firewall to remote IP), and the Cloud Connect (by removing IP from Firewall)
| Check Logs on Cloud Server | Pending | One error about name not matching when restarting gateway service. Resolved by updating httpd.conf
| Check SMP Logs | Pending | Nothing of note in the logs when checked at 11:35am, Sunday for last hour.
| Confirm documented site configuration | Pending
| Confirm Agent Settings | Pending
Upgrade Terminal Server | Uninstall old ActiveX components | Pending | Uninstall "Symantec Management Console ActiveX components 7.5 (x86)"
| Install new ActiveX components | Pending | Install "Symantec Management Console ActiveX components 7.5 (x86)"
Report Changes | Delete reports as detailed user requirement documentation | Pending | Remove specified reports from "Console Worker" folder
IT Analytics | Check cube processing | Pending | Many cubes now enabled for processing post-upgrade. Enabled them all.
| Check available cubes | Pending | Computer cube missing. Added cube. Errors in Cube Processing. Raise Case with Symantec Support
Check Fresh Build | Deploy New Machine | Pending
| Check Agent install and successful upgrade | Pending | Still need to check this on VM. Should be finished.
DST User Acceptance | 1. Remote Control | Pending | Tested successfully using test account (same rights as user support tech team)
| 2. Searching -(a) Partial asset tag | Pending | Tested successfully using "9999" and found 2 machines
| 2. Searching -(b) user name | Pending | Tested "Last Logon User" with "Mat" and found 3 results
| 2. Searching -(c) IP Address | Pending | Tested with staff subnet and had 154 return hits
| 2. Searching -(d) MAC Address | Pending | Tested with above and "OC" and got 3 hits (VMs)
| 2. Searching -(e) DOMAIN | Pending | Tested with IP filter and staff domain… 131 hits
| 2. Searching -(f) Export to CSV | Pending | Added privilege to "Create Reports". This added CSV icon to filters and enabled saving to CSV.
| 3. Reports -> Console Worker Reports -> Admin 'ictst' passwords | Pending | ok
| 4. Resource Manager -Basic inventory | Pending | ok
| 5. Delete Computers | Pending | Tested successfully on Managed Resource
6. The Console Worker Reports
| -->Local Admin ictst passwords | Pending
| -->CONNECT Pilot Group | Pending
| -->Computers Currently Enabled for Cloud Management | Pending
| -->Auto-Deleted Computers | Pending
| -->Add Remove Programs by Name | Pending | IT Analytics Impersonation Failure
| -->Add Remove Programs Search | Pending | IT Analytics Impersonation Failure
7. Resource Manager > Inventory
| --> Add Remove Program | Pending
| --> BIOS | Pending
| --> User accounts | Pending
8. Resource Manager
| --> Event logs | Pending
| --> AexClientLogon | Pending
User Changes | Reset User Setting profiles in CMDB | Pending | This sets users back to the portal page and wipes navigation history. Deleted 3660 rows
Finalise Upgrade (Success) | Commit Snapshots
| --> Remove Snapshot on SMP | Pending
| --> Remove Snapshot on SQL Server | Pending
| Open up firewall to all clients | Pending | Enable "World-Wide Web Services (HTTP Traffic-In)"
|  | Pending | Enable "World-Wide Web Services (HTTPS Traffic-In)"
|  | Pending | Enable "Symantec Management Platform CEM Incoming"
|  | Pending | Enable "Altiris Task Service Tickle (TCP 50123)
|  | Pending | Enable "Altiris SMP task Service (TCP 50124)
|  | Pending | Disable Maintenance Firewall rules
| Check SMP Logviewer | Pending
| Review Disk Space on SMP | Pending | 12GB free. Nothing to worry about for a few months. Request disk expansion for 3 months time.
Finalise Upgrade (Failure) | Revert Snapshots
--> Revert Snapshot on SMP
--> Revert Snapshot on SQL Server
Email out success

## 8.0HF5 Known Issues
Below are the issues listed for IT Management Platform 8.0 HF5 (DOC 9490, updated 19th Jan 2017)
Issue Evaluation: Nothing here applicable to our environment. Cleared for upgrade on 20th Jan by ILA
Applicable? | Solution | Known Issue Description | Article
No | Notification Server | Symantec Installation Manager is unable to install HF release on Notification Server N/A because modifying the web.config file fails. This problem occurs only if you have modified the security settings of the Default web site. Workaround: Before installing the IT Management Suite 8.0 HF5, remove the security setting of the Default web site from the web.config file. After completing the installation, add the security settings back. | N/A
No. We do not yet use Peer-to-peer | Notification Server | If you are using peer-to-peer downloading feature in ITMS 7.6HF7 (enabled through N/A a point-fix), you must save any customization that you have made to the settings and restore them manually after upgrading to ITMS 8.0HF5 release, because peer-to-peer downloading settings are reset to default during the upgrade. | N/A
No. Do not use Server inventory Packs | Inventory | When you upgrade the 7.x Inventory Pack for Servers Plug-in to 8.0 HF5, inventory N/A task configuration files for the following predefined server inventory policies are removed from the InvTaskConfig folder: ■ Collect Full Server Inventory ■ Collect Delta Server Inventory In such case, you can gather server inventory using Involn.exe/fsi or InvSoln.exe/dsi only after you successfully run the predefined server inventory policies on your client computers. | N/A
No. Do not have Macs | Inventory | You cannot view the names for some software components previously discovered on N/A Mac computers after the Inventory Plug-in is upgraded to 8.0 HF5 and software inventory is collected for the first time after the upgrade on these computers. The software component names get displayed on the user interface after the NS.Daily task successfully runs at 2:10 A.M. by default. | N/A
No. We do not use superscendence | Software Mgmt | The supersedence settings of a Managed Software Delivery policy work inconsistently N/A in the following cases: ■ A software resource has a dependency on some Software Update or Service Pack. ■ A software resource has a loop in its supersedence dependency. | N/A
No. We do not use replication | Software Mgmt | After you run standalone Item Replication Rule to migrate new Managed Software N/A Delivery policies or software delivery tasks, software package source is not distributed on target client computers. You need to import the required software packages to the target Notification Server again using the Software Resource Replicator utility. Note that you must uncheck the option Do not import resources which already exists in NS | N/A

## 8.1 Known Issues
As part of EAP, no known issues.