## How to Use SC
AA Implementation Baseline
_ WHEN making changes in the WBS - to envs. scope, etc. _ ONLY use Column D for values input
_ 20171114 _ v1
_ Determine if Solution is full AA implementation - comprised of both SA & RA, or only 1 of the two products
_ IF ONLY 1 of the products is implemented
- change all cells for the respective product - Column D, to zero (0) value in the AA_SolCalc WBS tab

## Assumptions
ASSUMPTIONS
_ Implementation Baseline assumes ONLY OOTB flows and use cases outlined in WBS are deployed
_ ANY variation from this => in a CUSTOM Solution Deployment
_ this is a T&M, Managed Project - PM @ 20% of Technical Time
_ HA - High Availability
up to 2 systems in DEV
up to 4 systems in ANY OTHER Env.
For HA - check the latest DB HA strategy & supported DB REPLICATION method, per PSM & Product Docs.
_ Environments Effort - Deployment
UAT - 75% off DEV
QA/PERF/TEST - 60% off DEV
PROD - 50% off DEV
_ DR is not included
_WBS only has 2 envs & PROD assistance
for more environments, derive the EFFORT for QA - to determine effort for QA+PERF+TEST environments
Column E has the details for QA
when deploying the solution in more than 3 envs - DEV, UAT & PROD - use values in Column E, in addition to overall effort
_ < OTHER ASSUMPTIONS to be inserted here >

## AA_SolCalc WBS
Task Name
CLIENT _ AA Deployment & Implementation | HOURS |  |  |  | HOURS | HOURS | HOURS
TOTAL Project Effort | 534 |  |  |  | Architect | Sr. Consultant | PM | TOTAL - incl. PM
Stage 1 - Project Setup and Initiation | 20 |  |  |  | 178 | 328 | 101.2 | 607.2
Develop Project schedule |  |  | 8
Identify Customer staff associated with the technology and processes to be reviewed |  |  | 4
Provide ALL existing documentation to CA |  |  | 4
Plan & conduct kickoff meeting |  |  | 4
Stage 2 - Requirements | 114
Current State Analysis - AA _ SA + RA |  | 46
Review the documented objectives of the initial implementation. FOR UPGRADE - validate Req's and identify changes between those objectives and the current Customer objectives |  |  | 10 | 16H for upgrades
Strong AuthN (SA) - Identify / Validate Requirements - Interview Customer personnel to validate new business requirements. For UPGRADE - identify/validate changed business Req's |  |  | 12
Risk AuthN (RA) - Identify / Validate Requirements - Interview Customer personnel to validate new business requirements. For UPGRADE - identify/validate changed business Req's |  |  | 12
Review the organization responsible for the daily operations of the CA products / technologies to understand the structure, responsibilities and tasks |  |  | 4
Collect and review relevant documentation with respect to the Customer's existing processes, technologies, and initiatives related to the selected CA technologies |  |  | 8
OOTB deployment _ approx. 10 Controllers (JSP files) - no changes / PROPERTIES file
Strong AuthN (SA) Use Cases (UC) - Baseline - FLOW Artifacts to be provided |  | 16
Authentication UC - CA Mobile OTP |  |  | 8
Credentials Issuance UC - CA Mobile OTP & Server OTP |  |  | 8
Additional OTP UC - NOT included in Baseline
QnA OTP |  |  | 0 | start with 4H per OOTB UC
OATH OTP |  |  | 0
EMV (Europay, Mastercard & Visa) OTP _ Proprietary tokens |  |  | 0
Document Requirements SA - outcome - SA Requirements Document _ IF SA+RA are part of the solution =>the 2 Req's Docs are combined - effort is the sum of the two sections |  | 26
Requirements document |  |  | 20 | simpler implementations - could lower time
Review Requirements document |  |  | 2
Include feedback & release Requirements document |  |  | 4
Document Requirements RA - outcome - RA Requirements Document _ IF SA+RA are part of the solution =>the 2 Req's Docs are combined - effort is the sum of the two sections |  | 26
Requirements document |  |  | 20 | simpler implementations - could lower time
Review Requirements document |  |  | 2
Include feedback & release Requirements document |  |  | 4
Stage 3 - Design | 64
Implementation - Options & Analysis |  | 8
Determine options, compare & select implementation path |  |  | 2
Review implementation path - SA, RA or SA+RA |  |  | 2
Include feedback, approve and release implementation path - based on steps in Build & Integrate stage |  |  | 4
Functional Design SA - outcome - SA Functional Design Document _ IF SA+RA are part of the solution => the 2 FD Docs are combined - effort is the sum of the two sections |  | 20
Functional Design document |  |  | 16 | simpler implementations - could lower time
Review Functional Design document |  |  | 2
Include feedback & release Functional Design document |  |  | 2
Functional Design RA - outcome - RA Functional Design Document _ IF SA+RA are part of the solution =>the 2 FD Docs are combined - effort is the sum of the two sections |  | 20
Functional Design document |  |  | 16 | simpler implementations - could lower time
Review Functional Design document |  |  | 2
Include feedback & release Functional Design document |  |  | 2
Technical Design SA - outcome - SA Technical Design Document _ IF SA+RA are part of the solution =>the 2 TD Docs are combined - effort is the sum of the two sections |  | 8
Technical Design document |  |  | 4
Review Technical Design document |  |  | 2
Include feedback and release Technical Design document |  |  | 2
Technical Design RA - outcome - RA Technical Design Document _ IF SA+RA are part of the solution =>the 2 TD Docs are combined - effort is the sum of the two sections |  | 8
Technical Design document |  |  | 4
Review Technical Design document |  |  | 2
Include feedback and release Technical Design document |  |  | 2
Stage 4 - Build & Integrate _ up to 2 pre-PROD envs. | 268
Install & configure SA infrastructure - CA Strong Authentication Server, Administration Console, User Data Service, Authentication Java SDK, Credential Management Java SDK, User Management Web Service, Authentication Web Service, Credential Management Web Service, Sample Application, SA Database |  | 102
Install SA systems - DEV |  |  | 16
Configure SA systems - DEV |  |  | 24
Install SA systems - UAT |  |  | 12 | 9.6 | Install SA systems - QA
Configure SA systems - UAT |  |  | 18 | 14.4 | Configure SA systems - QA
Configure HA & replication |  |  | 24
Run systems burn-in cycle(s) & monitoring |  |  | 8
Install & configure RA infrastructure - CA Risk Authentication Server, <other RA items to list> |  | 102
Install RA systems - DEV |  |  | 16
Configure RA systems - DEV |  |  | 24
Install RA systems - UAT |  |  | 12 | 9.6 | Install SA systems - QA
Configure RA systems - UAT |  |  | 18 | 14.4 | Configure SA systems - QA
Configure HA & replication |  |  | 24
Run systems burn-in cycle(s) & monitoring |  |  | 8
Data migration _ For UPGRADES only |  | 0 |  |  | Proposed UPGRADE hours - lines 69 - 75
Apply migration scripts - user data & SA/RA configurations migration ONLY |  |  | 0 |  | 12H
Migrate files & flows / configurations |  |  | 0 |  | 8H
Analyze migration results - verify logs & script migration errors |  |  | 0 |  | 4H
Solution - data migration (user data & user pwd data), timing & interactions planning |  |  | 0 |  | 12H
Final planning & Anaylsis of anticipated impact of implementing changes |  |  | 0 |  | 4H
Build feedback into migration plan |  |  | 0 |  | 4H
Final high-level plan for implementing the changes |  |  | 0 |  | 2H
Test plan in pre-production environment |  | 64
Test plans - SA |  |  | 24
Test plans - RA |  |  | 24
Refine test plans for PROD implementation scenario |  |  | 4
Refine implementation OR migration plan, timing & error logging + actions based on final pre-prod testing |  |  | 4
Final review - implemantation OR migration plan and approach updates - for Production implementation |  |  | 8
Test applications in pre-production environment _ For UPGRADES only |  | 0 |  |  | Proposed UPGRADE hours - lines 83 - 85
Test applications w/ migrated data |  |  | 0 |  | 8H
Complete (applications & systems) soak / load tests |  |  | 0 |  | 8H
Complete AA systems/DB burn-in time |  |  | 0 |  | 4H
Stage 5 - Deploy _ if PROD is not in scope, ONLY use the PROD Assistance line | 60
Product Deployment Assistance |  | 0 |  | _ recommended 40H per product
SA Production Assistance |  |  | 0
RA Production Assistance |  |  | 0
Product Deployment - stage 1, prior to go-live date (1 week ahead is recommended) |  | 56
Prepare Change Management requests for pre go-live date |  |  | 4
Install SA systems - PROD |  |  | 8
Configure SA systems - PROD |  |  | 12
Install RA systems - PROD |  |  | 8
Configure RA systems - PROD |  |  | 12 |  | Proposed UPGRADE hours - lines 96 - 99
Execute migration scripts - pre go-live _ For UPGRADES only |  |  | 0 |  | 12H
Analyze data migration logs & execution time - pre go-live _ For UPGRADES only |  |  | 0 |  | 12H
Prepare Change Management requests for go-live date |  |  | 0 |  | 4H
Test applications w/ migrated data |  |  | 0 |  | 12H
Complete AA systems/DB burn-in time |  |  | 8
Go-Live readiness assessment - Go / No-Go decision |  |  | 4
Product Deployment - stage 2, go-live date |  | 4 |  |  | Proposed UPGRADE hours - lines 103 - 105
Execute migration scripts - go-live _ For UPGRADES only |  |  | 0 |  | 8H
Analyze data migration logs & execution time _ For UPGRADES only |  |  | 0 |  | 4H
Final tests for applications w/ migrated data _ For UPGRADES only |  |  | 0 |  | 8H
Go-Live readiness assessment - Go / No-Go decision |  |  | 4
Production Assistance - post Go-Live _ 40H recommended if applicable |  | 0 |  | _ applicable only if requested by Client
Stage 6 - Project Handoff and Closure | 8
During this Stage, the CA project manager will conduct a Project closure meeting or call to close out these activities |  |  | 8
TOTAL Project Effort | 534